| TASHYID URBAN DEVELOPMENT | ALYA TOWER -- PROJECT STATUS REPORT Sidra Corniche Fund ¦ Jeddah, Saudi Arabia | 15-Jun-2026 Period: June 2026 ● OVERALL: AMBER |
| --- | --- | --- |

| PROJECT MANAGER | CURRENT PHASE | LOCATION | TOWER SCALE | FUND MANAGER |
| --- | --- | --- | --- | --- |
| Abdullah Anbar | Phase 1 - Design and Funding | Corniche, Jeddah | 65 Units ¦ 29 Floors | Sidra Capital |

| MAIN CONTRACTOR | LEAD DESIGNER | SUPERVISION AND PM | FUND MANAGER | BRANDING AGENCY |
| --- | --- | --- | --- | --- |
| UCCL | Erga | Midrar | Sidra Capital | Brandship (contract pending) |

| PROJECT SNAPSHOT | KEY ACHIEVEMENTS THIS PERIOD |
| --- | --- |
| Brief: Premium residential tower on Jeddah's North Corniche waterfront. Location: Corniche Road, North Jeddah, Saudi Arabia Units: 65 exclusive residences (redesigned from original 30) Height: 29 floors above ground level Phase: Phase 1 of 3 -- Design and Funding (Apr - Jul 2026) Landowner: HH Prince Mohammed bin Abdullah Al Saud Developer: Tashyid Urban Development (TUD) | > Erga schematic design completed -- Midrar review comments shared > Substructure and superstructure (structural works) complete > Excavation works commenced on site > Sidra Capital loan term sheet received (under review) > Brandship branding agency proposal finalised -- awaiting contract > Site fence rehabilitation in progress (20% complete) > Site signboard installation planned for 14-Jun-2026 |
| BUDGET STATUS | NEXT STEPS (2-4 weeks) |
| ITEM AMOUNT (SAR) Approved Budget TBC -- Pending Sidra loan finalisation Spent to Date TBC -- Finance team to confirm Forecast Final Cost TBC -- Under review with Sidra Capital Contract Values on File TBC (pending Finance input) --------------------------------------------------- Budget RAG Status: AMBER Note: Financial baseline locked upon Sidra loan approval. CEO and investor decision required to unblock (91 days open). | 1. Finalise Midrar and Sidra development contracts Owner: Abdullah Anbar ¦ Due: 30-Jun-2026 ¦ From MOM 08-Jun 2. Resolve Sidra Capital loan term sheet -- escalate to CEO Owner: Abdullah Anbar ¦ Due: URGENT -- 91 days open 3. Sign Brandship branding and marketing contract Owner: Renad Rajab ¦ Due: 30-Jun-2026 4. Initiate NWC Developers Agreement (obtain Amana letter first) Owner: Abdullah Anbar ¦ Due: Jul-2026 |
|  | DECISIONS REQUIRED |
|  | 1. SIDRA LOAN TERM SHEET APPROVAL -- CEO and Investor Action Required Loan term sheet with Sidra Capital is 91 days open, blocking the fund announcement and financial baseline. CEO escalation required urgently. 2. Sales Price Sheet -- FMH Review and CEO Approval Price sheet must be adjusted per FMH comments before public release. |

TASHYID URBAN DEVELOPMENT ¦ www.tashyid.sa ¦ Info@tashyid.sa ¦ +966 12 612 6277 ¦ CONFIDENTIAL -- CEO and Investor Use Only