| TASHYID URBAN DEVELOPMENT | ALYA TOWER -- PROJECT STATUS REPORT Sidra Corniche Fund ¦ Jeddah, Saudi Arabia | 15-Jun-2026 Period: June 2026 ● OVERALL: AMBER |
| --- | --- | --- |

| PROJECT MANAGER | CURRENT PHASE | LOCATION | TOWER SCALE | FUND MANAGER |
| --- | --- | --- | --- | --- |
| Abdullah Anbar | Phase 1 - Design and Funding | Corniche, Jeddah | 65 Units ¦ 29 Floors | Sidra Capital |

| MAIN CONTRACTOR | LEAD DESIGNER | SUPERVISION AND PM | FUND MANAGER | BRANDING AGENCY |
| --- | --- | --- | --- | --- |
| UCCL | Erga | Midrar | Sidra Capital | Brandship (contract pending) |

| PROJECT OVERVIEW | PROGRESS THIS MONTH |
| --- | --- |
| Alya Tower is a 29-floor luxury apartment building planned for the North Corniche in Jeddah -- one of the city's most prestigious waterfront locations. The tower will deliver 65 premium residences, expanded from an earlier plan of 30 units to better reflect the site's full potential and current market demand. The land is owned by HH Prince Mohammed bin Abdullah Al Saud. Tashyid Urban Development (TUD) is leading the development on his behalf. The project has three phases. We are currently in Phase 1 (April to July 2026), which covers finalising the architectural design and securing the project's funding. Construction is planned to begin in January 2027 and complete by May 2029. | > The full architectural drawings for the tower are complete and have been independently reviewed by the supervision team > The building's underground foundations and main structural frame are already in place on site -- significant early work is done > Ground excavation has started -- physical activity is visible and underway on site > The project's lender (Sidra Capital) has submitted a funding proposal -- it is currently under review > A branding and marketing agency (Brandship) has been selected -- their contract is being finalised > The site perimeter fence is being upgraded -- 20% complete > A new project signboard is planned for installation on 14-Jun-2026 |
| FINANCIAL STATUS | WHAT HAPPENS NEXT |
| The project's total budget has not yet been confirmed. This is because the funding agreement with Sidra Capital -- the company that will finance the development -- has not been signed despite being open for 91 days. Until that agreement is finalised, no firm budget can be set, no supplier contracts can be fully awarded, and the project cannot be announced to the public. Financial Status: AMBER (Attention Required) Resolving the Sidra Capital agreement is the single most urgent financial action for the CEO this month. | 1. Sign the supervision contract with Midrar (Due: 30-Jun-2026) Midrar is the firm responsible for overseeing all construction quality on site. Their contract must be signed before works can progress further. 2. Resolve the Sidra Capital funding agreement (URGENT -- 91 days open) The CEO must escalate directly with Sidra Capital to close this. It is blocking the entire financial plan of the project. 3. Sign the marketing contract with Brandship (Due: 30-Jun-2026) Brandship will handle the tower's brand identity and apartment sales. Their contract is ready to be signed. 4. Obtain the Amana municipal permit (Due: Jul-2026) An official letter from Jeddah municipality is required before the land development agreement can be formalised with the landowner. |
|  | DECISIONS NEEDED FROM CEO |
|  | 1. APPROVE THE SIDRA CAPITAL FUNDING AGREEMENT (CEO -- Urgent) Sidra Capital will provide the main financing for this project. Their proposal has been waiting for a decision for 91 days. Without this approval, the project cannot set sales prices, begin procurement, or make any public announcement. The CEO must contact Sidra Capital directly this week to resolve this. 2. APPROVE THE APARTMENT SALES PRICE LIST (CEO -- Review Required) A pricing plan for all 65 apartments has been prepared and reviewed. CEO approval is required before any sales conversations or public pricing can begin. |

TASHYID URBAN DEVELOPMENT ¦ www.tashyid.sa ¦ Info@tashyid.sa ¦ +966 12 612 6277 ¦ CONFIDENTIAL -- CEO and Investor Use Only